## Introduction

This is a general flow of how machine debug should be conducted and approximately in what order. Items might be skipped and/or partially completed to come back to later, or worked on concurrently with other items as the situation dictates. Some items may not be applicable for every machine.

- Initial Machine Inspection

☐ Power Supply

- Verify the machine is receiving proper voltage (verify with electrician).

- Check for any blown fuses or tripped breakers.

☐Machine Orientation Fit and Finish (verify with ME and/or builder)

- Ensure the machine is correctly positioned and aligned on the floor).

- Confirm all leveling feet are properly adjusted.

- Evaluate alignment, leveling, and fit of all stations.

- Pay special attention to stations that interact with each other or are collision hazards.

- Check all belt tension.

- Control System Initialization

☐Power Up Control Devices

- Load firmware.

- Set IP addresses.

- Load programs.

- Check communications

☐Commission Safety

- Check all input circuits for functionality. Make sure to toggle each device separately.

- Check output circuits for functionality and confirm safety works as intended.

- Bypass circuits as necessary ensuring that the DANGER signage is prominently posted.

- Any mounted Estop buttons must be functional, no bypasses allowed.

☐Check IO and Pneumatics

- Toggle all IO and verify it functions and is read/written correctly from PLC tags.

- Check for NO and NC inputs and polarity of outputs.

- Put air on the machine and check for leaks.

- Adjust pressure and flow controls as appropriate optimizing for cycle time and smooth operation.

☐Motion System Verification

- Tune servos.

- Home servos.

- Ensure proper scaling and motion polarity.

- Check for coupling issues, vibration, and interferences.

- Set torque limits to 50% as an initial value. If you get torque faults during debug, investigate and increase as necessary. Once the machine is running in full auto and meeting cycle, set this value approximately 20% over the max actual value.

☐Machine Controls Setup

- Calibrate applicable devices.

- Input starting setup parameters into the machine. Examples:

  - Servo motion parameters like speed, accel and decel.

  - Motion axis defined positions.

  - Verify all motion permissives. (Example: z axis is retracted before x axis motion is allowed)

  - Programmable sensor setup.

  - IO link or analog data configuration.

  - Known recipe parameters for the part that will be run first.

☐HMI Testing

- Verify screens are accessible.

- Check all tag connections are properly made.

- Check that buttons perform the desired outcome.

☐Test All Manual Functions Via the HMI

- Make sure to set servo speeds to start out slow.

☐Test Machine Operations with Manual Functions

- Where possible, test any machine operations with manual functions to verify the mechanics function as intended.

- Make any adjustments mechanical or electrical if issues are discovered.

☐Test Machine Subsystem Operations with Automatic Functions

- Set speeds slow.

- Test subsystems separately using a “single step” and “dry run” style approach (if possible) to verify the sequence.

- Once a subsystem passes the single step approach, test the system using a “full auto, dry run” approach. Limit the machine to one subsystem at a time (or the smallest multiple if they need to work together).

- After “full auto” is passed on a subsystem, slowly increase the speed until at least the point where the machine will meet cycle time or better.

- After dry run functionality is proven out. Restart the process with real parts.

- Perform fault checkout.

  - Make sure all messages are configured and useful.

  - Note any high occurrence or particularly disruptive faults and diagnose root causes, provide proactive fixes, or pursue design change when appropriate.

  - Add retry logic, automatic recovery, or automatic reject to increase machine uptime

- Make any adjustments mechanical or electrical if issues are discovered.

- As part of this process, define a set of “slow speed” setpoints for automatic mode along with the “running speed” setpoints. This makes toggling between fast and slow easy.

☐Test Full Machine Operations with Automatic Functions

- Use the same approach for testing subsystems to now test the full machine operation.

- Full safety system operation must be in place once core machine functions are proven out.

- Verify any required performance metrics are being calculated and displayed correctly.

- Setup remote access if applicable.

- Check for overlooked safety hazards.

- Remove unused tags, debug bits, AFI instructions, or temporary code.

☐Apply machine labels (Electrician Executes, Engineer Checks)

- Machine labels

- LOTO labels

- Disconnect and voltage info/warning labels

- Pinch point labels

- Laser light warning labels

- Any other applicable labels

☐Update Electrical and Mechanical Documentation.

- Update panel layout to match actual layout.

- Update drawings to match redlined version.

- Update BOM to match actual machine.

- Add any calibration procedures.

- Take backups of all software in “as shipped” condition.